# Vendah - Launch Readiness & Progress Report

Prepared 2 September 2026  |  Target: soft launch

------------------------------------------------------------

# 1. Executive Summary

The product is feature-complete for a first merchandise launch: storefront, checkout with card / three mobile-money rails / cash on delivery, order fulfilment, refunds & returns, discounts, shipping zones, tax, customer accounts, staff, analytics, marketing campaigns, homepage builder and SEO are built, committed and deployed to the production alias (https://vendah-blue.vercel.app).

We are not yet launch-ready. Four items stand between us and go-live, and all four are configuration/operations rather than code: (1) the root domain vendah.com is not registered, so no storefront is publicly reachable; (2) the Paystack secret key is missing from the Vercel production environment; (3) outbound email is still in mock mode (no Resend key); and (4) Supabase auth/SMTP is not configured. Section 4 contains the exact, order-of-operations checklist to clear these.

Estimated remaining effort once the domain is registered: approximately 1-2 hours of configuration plus a 60-minute end-to-end payment smoke test.

# 2. Progress Since Last Report

SEO: shipped platform sitemap.xml + robots.txt and per-subdomain route handlers; verified 200 on production and per-store context.

Cash on Delivery: migration 0039 added orders.payment_method and orders.payment_collected_at; full COD checkout branch (stock decrement, low-stock alerts, discount usage, confirmation + merchant emails); COD-ready success page; dashboard Mark payment received flow; COD orders excluded from stale-order auto-cancel.

Checkout hardening: Paystack webhook rewrite with signature validation, settlement + stock-decrement RPCs, transaction status API with mobile-money polling, stale-order expiry cron (once daily), transaction clean-up on failed initialisation.

Homepage builder: five prebuilt templates with a template picker modal and replace/append confirmation.

Dashboard UX: sidebar hover pop-out, instant loading skeleton for all navigation, splash overlay reduced from 3.5s to 0.8s and made non-blocking.

Database: repaired migration history (0017-0038) and applied 0039 to the production Supabase project.

Housekeeping: all work committed and pushed (87b2009); 92 unit tests passing; TypeScript clean.

# 3. Launch-Readiness Review

| Area | Assessment | What is required |
| --- | --- | --- |
| Domain & public storefront URLs | BLOCKING | vendah.com unregistered; every storefront subdomain currently returns NXDOMAIN. |
| Online payments (card + mobile money) | BLOCKING | PAYSTACK_SECRET_KEY absent from Vercel Production env; every online checkout fails in production. |
| Email delivery | BLOCKING | sendEmail is in console/mock mode; RESEND_API_KEY and EMAIL_FROM absent; Supabase SMTP not set up. |
| Core retail feature set | READY | Storefront, checkout, COD, orders, fulfilment, refunds/returns, discounts, shipping, tax, customers, staff, analytics, marketing, homepage builder, SEO, plan gating. |
| Code health | READY | TypeScript clean, 92/92 unit tests pass; lint has only pre-existing warnings in untouched files. |
| End-to-end payment testing | CAVEAT | Webhook to settlement flow not yet exercised on production; a manual smoke test is mandatory before launch. |
| Monitoring & observability | CAVEAT | No error tracking or uptime alerts yet (optional before launch). |

# 4. Launch Configuration Checklist

Work the groups top-to-bottom (A to G). Each row states the exact location or command. Tick the Done column as items complete.

## A. Domain & DNS

| # | Task | Exact step / location | Done |
| --- | --- | --- | --- |
| A1 | Register the root domain | Register vendah.com at any registrar (GoDaddy, Namecheap, Porkbun). | ☐ |
| A2 | Add the root domain to the Vercel team | Run: vercel domains add vendah.com | ☐ |
| A3 | Add the domain to the project | Run: vercel project add-domain vendah.com | ☐ |
| A4 | Point the apex record at Vercel | Vercel project > Settings > Domains: add A record @ = 76.76.21.21 | ☐ |
| A5 | Create the wildcard for storefronts | At the registrar: CNAME *.vendah.com = cname.vercel-dns.com | ☐ |
| A6 | Point site URL at the real domain | Set NEXT_PUBLIC_SITE_URL = https://vendah.com (currently the Vercel alias). | ☐ |
| A7 | Verify | dig vendah.com +short and open https://mensfit.vendah.com/ in a browser (replace mensfit with a real tenant). | ☐ |

## B. Environment variables (Vercel Production)

Vercel > Project > Settings > Environment Variables. Add each, then trigger a production redeploy (vercel --prod) at the end of this group.

| # | Task | Exact step / location | Done |
| --- | --- | --- | --- |
| B1 | Paystack live secret key | PAYSTACK_SECRET_KEY = copy from Paystack Dashboard > Settings > API Keys & Webhooks (Secret key). | ☐ |
| B2 | Resend API key | RESEND_API_KEY = copy from Resend > API Keys. | ☐ |
| B3 | Email sender address | EMAIL_FROM = Vendah <no-reply@shop.vendah.com> (must match a verified Resend domain). | ☐ |
| B4 | Confirm existing variables present | NEXT_PUBLIC_SUPABASE_URL, NEXT_PUBLIC_SUPABASE_ANON_KEY, SUPABASE_SERVICE_ROLE_KEY, NEXT_PUBLIC_SITE_URL, NEXT_PUBLIC_APP_DOMAIN, CRON_SECRET. | Present |
| B5 | Redeploy after env changes | Run: vercel --prod and confirm the build log loads the new variables. | ☐ |

## C. Supabase project csiidtotrilwlzesudxv

| # | Task | Exact step / location | Done |
| --- | --- | --- | --- |
| C1 | Set the site URL | Supabase > Authentication > URL Configuration: Site URL = https://vendah.com | ☐ |
| C2 | Allowlist redirect URLs | Add to Redirect URLs: https://vendah.com/**, https://vendah-blue.vercel.app/**, http://localhost:3000/** | ☐ |
| C3 | Enable custom SMTP (password resets / sign-up confirmations) | Authentication > Providers > Email: enable Email, choose SMTP, use the Resend SMTP host (smtp.resend.com, port 465). | ☐ |
| C4 | Match sender with the Resend domain | Set the SMTP sender name/email to no-reply@shop.vendah.com. | ☐ |
| C5 | Keep confirmation strict | Confirm Confirm email is enabled (no auto-confirm) for production sign-ups. | ☐ |

## D. Paystack payments

| # | Task | Exact step / location | Done |
| --- | --- | --- | --- |
| D1 | Validate the secret key in TEST mode first | Flip the Paystack dashboard to Test mode, paste the test Secret key as PAYSTACK_SECRET_KEY, redeploy, and complete a test purchase. | ☐ |
| D2 | Register the webhook | Paystack Dashboard > Settings > API Keys & Webhooks: Webhook URL = https://vendah.com/api/webhooks/paystack | ☐ |
| D3 | Confirm webhook signature checks | Code review src/app/api/webhooks/paystack/route.ts - verify it validates x-paystack-signature. | ☐ |
| D4 | Connect merchant subaccounts | Each merchant connects Paystack via Dashboard > Payments (sets tenants.paystack_subaccount_code), or create subaccounts and backfill the column. | ☐ |
| D5 | Switch to LIVE mode | Paystack dashboard to Live, set the Live key as PAYSTACK_SECRET_KEY, redeploy, rerun a card and a mobile-money purchase. | ☐ |

## E. Resend email delivery

| # | Task | Exact step / location | Done |
| --- | --- | --- | --- |
| E1 | Add the sender domain | Resend > Domains: add shop.vendah.com and add the SPF/DKIM DNS records it returns at the registrar. | ☐ |
| E2 | Wait for domain verification | Resend shows the domain as Valid; only then emails are deliverable. | ☐ |
| E3 | Send a real test email | Trigger an order confirmation from the end-to-end test and confirm delivery to a real inbox. | ☐ |

## F. Cron & operations

| # | Task | Exact step / location | Done |
| --- | --- | --- | --- |
| F1 | Confirm the daily job | Vercel > Settings > Cron Jobs: /api/cron/expire-orders on schedule 0 4 * * * active (hobby allows 1/day). | ☐ |
| F2 | Optional: error monitoring | Add Sentry (dashboard + storefront) for crash visibility before public traffic. | ☐ |
| F3 | Remove fabricated marketing stats | Replace the placeholder numbers on the landing page and sign-in/sign-up panels (src/app/page.tsx and the (auth) pages). | ☐ |

## G. End-to-end smoke test (production)

| # | Scenario | What success looks like |
| --- | --- | --- |
| G1 | Card purchase | Test card 4084 0840 8408 4081: payment settles via webhook, stock decrements, order confirmation + merchant emails arrive. |
| G2 | MTN Mobile Money purchase | Test number: transaction shows pending, the status API resolves it to paid, order settles. |
| G3 | Cash on Delivery purchase | Order created pending with payment_method=cod; confirmation email sent; dashboard shows Mark payment received; payment_collected_at stamped. |
| G4 | Refund flow | Refund from Dashboard > Payments settles on Paystack and order reflects the refund. |
| G5 | Password reset / sign-up confirmation | Both emails arrive and links work from the production URL. |
| G6 | Staff invite email | Invited member receives the invite and can sign in. |
| G7 | Cart recovery email | Manual send from Cart Recovery lands in the shopper inbox. |
| G8 | Subscription lifecycle | Plan charge webhook creates the subscription; expired subscription triggers downgrade. |
| G9 | Storefront SEO | https://mensfit.vendah.com/sitemap.xml and /robots.txt return 200 with tenant content. |
| G10 | Mobile / PWA | Storefront passes on a real phone; install prompt works. |

# 5. Open Items & Recommendations

Register vendah.com - the single external dependency that unlocks everything (A1-A7).

Add the three missing environment variables (B1-B3) and redeploy.

Disable auto-confirm email and keep Supabase SMTP on the Resend sender domain.

Replace the fabricated landing/sign-in metrics with real numbers before public traffic.

Optional but recommended: a Playwright end-to-end suite covering the pay -> webhook -> settle -> stock path, and Sentry error monitoring.